## Summary
Objectives:
<Objectives>
Test Strategy:
<Description about the test trategy>
Scenarios:
<High Level description>
Metrics:
<which metrics are you going to use>
Milestones:
|  | Start Date | EndDate
SmokeTest
CRUD
Team Members:
Marilyn Moya
Silvia Valencia
Yesica Acha

## Scenarios
Images describing the scenarios

## Services
Method | endpoint | ToBe Tested? | Comments
POST | projects | Yes |  | Yes
GET | projects | Yes
PUT | projects | Yes
DELETE | projects | Yes
POST | items | Yes |  | No
GET | items | Yes
PUT | items | Yes
DELETE | items | Yes
POST | users | Yes
GET | users | Yes
PUT | users | Yes
DELETE | users | Yes
GET | filters | No
GET | icons | No
Describe the list of Services
available in the product

## Smoke Test
TestID | Services Related to | Method | endpoint | Comments | Owner | Priority | Complexity
| users | GET | /users.json |  | Yesica | 1
| projects | GET | /projects.json |  | Silvia | 1
| items | GET | /items.json |  | Marylin | 1

## CRUD
TestID | Services Related to | Method | endpoint | Comments | Owner | Priority | Complexity
| users | GET | /user.json | Get user | Yesica | 1
| users | POST | /user.json | Create a user | Yesica | 1
| users | POST | /user.json | Create user with invalid values | Yesica | 1
| users | PUT | /user/0.json | Update user | Yesica | 1
| users | PUT | /user/0.json | Update user with invalid values | Yesica | 1
| users | DELETE | /user/0.json | Delete user | Yesica | 1
| projects | GET | /projects/[id].json | Get project by id | Silvia | 1
| projects | POST | /projects.json | Create a project | Silvia | 1
| projects | POST | /projects.json | Create a project with invalid values | Silvia | 1
| projects | PUT | /projects/[id].json | Update a project | Silvia | 1
| projects | PUT | /projects/[id].json | Update a project with invalid values | Silvia | 1
| projects | DELETE | /projects/[id].json | Delete project | Silvia | 1
| items | GET | /items/[id].json | Get item by id | Marylin | 1
| items | POST | /items.json | Create new item | Marylin | 1
| items | POST | /items.json | Create new item with an invalid project id | Marylin | 1
| items | PUT | /items/[id].json | Update item by id | Marylin | 1
| items | PUT | /items/[id].json | Update item with an invalid Parent Item Id | Marylin | 1
| items | DELETE | /items/[id].json | Delete item by id | Marylin | 1

## BDT
TestID | Services Related to | Scenario Title | Owner | Comments | Priority | Complexity | NA
| resources | Scenario 1 | xxx |  |  |  | Planned
| resources | Scenario 2 | yyy |  |  |  | In Progress
Blocked
Yes

## Reports
The reports that represents
the progress should be here

## Parameters in General
Complexity | Hours estimated | Description
Low
Medium
High
Test Case Status
NA
Planned
In Progress
Blocked
Yes
Test Cases Priority
1
2
Services
projects
users
items